## Sheet1
T1 W1-2 & Project specification \\ \hline
T1 W1-2 & Development tooling research \\ \hline
T1 W3-9 & Begin development of website foundation \\ \hline
T1 W4 & Design basic UI \\ \hline | Event | Start Week | End Week
T1 W5-7 & User authentication \\ \hline | Project Specification | 1 | 2
T1 W8-9 & Integration with PlaidAPI \\ \hline | Development tooling research | 1 | 2
T2 W1 & Testing of website foundation \\ \hline | Development of website foundation | 3 | 9
T2 W2-10 & Repeated strategy development* \\ \hline | Design basic UI | 4 | 4
Easter & Finishing touches \\ \hline | User authentication | 5 | 7
Throughout & Document research \\ \hline | Integration with PlaidAPI | 8 | 9
T3 W1 & Dissertation due \\ \hline | Testing of website foundation | 11 | 11
| Repeated strategy development | 12 | 20
| Finishing touches | 21 | 21
| Document research | 1 | 22
| Dissertation due | 22 | 22